## ELA-Maintenance-Support_Oct2021
| Best | Exp | Worst
#REF!
Remaining work tasks | 1.25 | 2.25 | 3.75 | Itemeized work listed in each row below
| 0.25 | 0.5 | 0.75 | Update Pop-Up timing, add 3 links/buttons that currently display at end of placement test on Pop-Up
| 0.5 | 0.75 | 1 | Blog Sidebar Update: Add button/links - total of 6 to different class types
| 0.5 | 1 | 2 | Blog Publish. Turn on page, turn on navigation, publish posts
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Website Support | 8 | 14 | 20
estimated hours per month | 1 | 3 | 5 | Blog Support — any blog publishing related issue
| 1 | 2 | 3 | Coupon/Pop-Up Support — setup/congfiguration issues
| 3 | 4 | 5 | Login Support — students having login related issues
| 1 | 2 | 3 | User Experience Support — any UX related issues
| 2 | 3 | 4 | Payment Support — WooCommerce/Paypal related issues

## Sept-2021 Work
| Best | Exp | Worst
#REF!
Blog Setup | 3.25 | 5.5 | 9.5 | Moving exiting site over to WPEngine under A+L control
| 0.75 | 1 | 2 | Setup blog landing page to work like Lingoda
| 0.5 | 0.5 | 0.5 | Create categories needed to start blog for filtering and categorization
| 0.5 | 1 | 2 | Create one sample blog post (minimal) for each category to test blog landing page and category landing pages
| 0.5 | 1 | 2 | Create category landing page template—will allow the site to display ONLY Academic related posts, ONLY Business English posts, etc.
| 1 | 2 | 3 | Visually style all new pages and posts (Custom CSS) to make everything "fit" visually
| 1 | 2 | 2 | Check layout of blog landing page, category page, post page to confirm everything looks good responsively. Make needed fixes
Main Navigation | 1.5 | 2.5 | 3.5
| 0.5 | 0.5 | 0.5 | Put "Blog" into main navigation, confirm it points to the correct location | LearnDash Configuration
| 1 | 2 | 3 | View and Test menu responsively to make sure Blog appears properly in all viewports | - Paypal (ecommerce)
TOTAL | 4.75 | 8 | 13 | Totals are for all items above
Tutorial Videos | Best | Exp | Worst | How long is the video tutorial? Length of video determines effort
| 1 | 1.5 | 2 | Short: ~5mins or less
| 1.5 | 1.75 | 2 | Medium: 6—15mins
| 2 | 2.25 | 3 | Long:15 mins or longer

## Sheet1
| Best | Exp | Worst
| 8 | 10 | 14
Wireframes | [6 empty] | ← these aren't dynamic - these are the same lines you see in our standard PERT estimate docs
Visual Design | 2 | 2 | 4 | Implementing current design and color scheme in Divi
Visual Design Revisions | 1 | 2 | 3 | Any modifications after beta site is ready
UI Production | 5 | 6 | 7 | Copying over site content, saving select items. Image selection, processing and production, any customization needed for WordPress
App Icon, Store artwork
| Best | Exp | Worst
| 62 | 96 | 138 | Totals are for all items below |  |  |  | 0
Domain Name
| 1 | 2 | 2 | —Purchase or transfer, and configure DNS
WordPress Server Setup | 8 | 13 | 22 | Moving exiting site over to WPEngine under A+L control
| 1 | 2 | 3 | —WPEngine server setup and configuration
| 2 | 3 | 5 | —Import preexisting database and confirm success | from existing website at http://elite-language.flywheelsites.com/
| 2 | 3 | 5 | —Import preexisting file system and confirm success | from existing website at http://elite-language.flywheelsites.com/
| 2 | 3 | 4 | —Import preexisting graphics and images and confirm success | from existing website at http://elite-language.flywheelsites.com/
| 1 | 2 | 5 | —Confirm preexisting configuration is working in all aspects of authentication, plugins, and settings and time to repair if needed
Plugins | 8 | 15 | 22
| 5 | 10 | 15 | —Install and configure plugins (can vary widely with degree of difficulty) |  | LearnDash Configuration
| 3 | 5 | 7 | —Test and Troubleshoot any plugin conflicts or other plugin errors |  | - Paypal (ecommerce)
Theme(s) | 9 | 15 | 22
| 5 | 8 | 12 | —Install and configure baseline setup
| 2 | 4 | 6 | —Customize theme based on required plugins: (additional pages; error, confirmation, carts, etc)
| 2 | 3 | 4 | —Troubleshoot any theme conflicts that come up in process of customization
Content | 18 | 25 | 34
| 2 | 2 | 3 | —Setting up all needed pages, awaiting content
| 1 | 1 | 2 | —Configure navigation menus to access all pages that have been setup
| 4 | 6 | 8 | —Layout and typesetting provided copywriting throughout website pages
| 2 | 3 | 4 | —Images: selection, sizing, editing, uploading, placement within content
| 2 | 3 | 3 | —Video: selection, sizing, editing, uploading, placement within content
| 1 | 1 | 1 | —Other Documents: selection, sizing, editing, uploading, placement within content
| 3 | 5 | 8 | —Translation implementation and configuration
| 3 | 4 | 5 | —Editing content after client review on development site
Testing and Quality Assurance | 10 | 13 | 17
| 2 | 2 | 2 | —Navigate entire site. Confirm access to everything for each type of user.
| 2 | 2 | 2 | —Confirm that all content is presenting proprely no matter the viewport size (responsive)
| 1 | 1 | 2 | —Confirm that required content is protected by login where necessary (paid content, software, courses, etc.)
| 1 | 1 | 1 | —Confirm any ecommerce proesses are working successfully
| 4 | 7 | 10 | —Repair and resolve any final issues before launch
Launch | 9 | 15 | 21
| 1 | 1 | 1 | —Confirm and DNS changes are made to push development server to new "production" server
| 4 | 7 | 10 | —Repair and resolve any issues reported by internal team
| 4 | 7 | 10 | —Repair and resolve any issues reported by client and their team
TOTAL | 70 | 106 | 152